## PPR - June 26 2026
Medicaid Eligibility Partner
Progress week ending: June 26, 2026
Milestones |  |  | Status | % Complete | End Date
MSA and SOW fully executed — ElevatePFS partnership formalized (04/10–04/14/2026) |  |  | C | 100%
Kickoff meeting completed 05/21/2026 — weekly cadence with Elevate team established |  |  | C | 100% | 5/24/2026
Transition SP Estimate creation |  |  | G | 90% | 6/29/2026
Clearance/ Onboarding |  |  | G | 20% | 7/27/2026
Client System Access/Training |  |  | G | 50% | 8/3/2026
Create and send reconciliation Demo File |  |  | G | 50% | 7/2/2026
Finalization of 90 Day Lookback to send to Elevate |  |  | G | 75% | 6/26/2026
Finalize Daily Placement Files to Elevate |  |  | NS | 0%
Go Live Date |  |  | G | 10% | 8/10/2026
Project Team
Executive Sponsor: | Michelle Lewis |  | Project Manager: | Harrison Nemelka
Business Sponsor: | Rachel Seaman
Project Description
Augment RCO Patient Financial Navigation resources to increase Medicaid eligibility identification and coverage capture, thus reducing financial barriers to care and uncompensated care. Key components include establishing third party workflows and reporting, expanding coverage identification for uninsured and underinsured populations, and creating scalable processes that support both patient financial outcomes and organizational revenue capture.
Overall Status
G | Project is on track to meet milestone timelines.
Description |  |  | Target | Target Realized to Date | % of Target Realized
Self Pay to Medicaid Conversion |  |  | >20%
Medicaid Reimbursement |  |  | N/A
Approval Rate |  |  | >75%
Application Turnaround Time |  |  | N/A
Accomplishments |  | Next Steps |  | Issues
• MSA and SOW fully executed — ElevatePFS partnership formalized (04/10–04/14/2026) • Kickoff meeting completed 05/21/2026 — weekly cadence with Elevate team established • WQ 14856 Insured Inpatient - Prod 6/04 • BI 748 PFN Review Complete - Prod 6/04 • 90 day look back file specs • Epic Access Approved – Template creation beginning |  | • Transition Self-Pay Estimate creation - 6/29/2026 • Completion of 90-day lookback file • SFTP File Build Testing • Finalize internal team scope |  | • Elevate Epic Identification - Agency or BI
Status Legend
C | Complete
G | On Track
Y | At Risk
R | Significant Risk w/ inadequate mitigation
NS | Not Started

## PPR - July 24 2026
Medicaid Eligibility Partner
Progress week ending: July 24, 2026
Milestones |  |  | Status | % Complete | End Date
MSA and SOW fully executed — ElevatePFS partnership formalized (04/10–04/14/2026) |  |  | C | 100%
Kickoff meeting completed 05/21/2026 — weekly cadence with Elevate team established |  |  | C | 100% | 5/24/2026
Transition SP Estimate creation |  |  | C | 100% | 6/29/2026
Clearance/ Onboarding |  |  | C | 100% | 7/27/2026
Client System Access/Training |  |  | C | 100% | 8/3/2026
Create and send reconciliation Demo File |  |  | C | 100% | 7/27/2026
Finalization of 90 Day Lookback to send to Elevate |  |  | C | 100% | 6/26/2026
Finalize Daily Placement Files to Elevate |  |  | C | 100% | 8/10/2026
Elevate Notes file |  |  | C | 100% | 7/27/2026
Go Live Date |  |  | C | 100% | 8/10/2026
Project Team
Executive Sponsor: | Michelle Lewis |  | Project Manager: | Harrison Nemelka
Business Sponsor: | Rachel Seaman
Project Description
Augment RCO Patient Financial Navigation resources to increase Medicaid eligibility identification and coverage capture, thus reducing financial barriers to care and uncompensated care. Key components include establishing third party workflows and reporting, expanding coverage identification for uninsured and underinsured populations, and creating scalable processes that support both patient financial outcomes and organizational revenue capture.
Overall Status
G | Project is on track to meet milestone timelines.
Description |  |  | Target | Target Realized to Date | % of Target Realized
Self Pay to Medicaid Conversion |  |  | >20%
Medicaid Reimbursement |  |  | N/A
Approval Rate |  |  | >75%
Application Turnaround Time |  |  | 45 Days
Accomplishments |  | Next Steps |  | Issues
• MSA and SOW fully executed — ElevatePFS partnership formalized (04/10–04/14/2026) • Kickoff meeting completed 05/21/2026 — weekly cadence with Elevate team established • WQ 14856 Insured Inpatient - Prod 6/04 • BI 748 PFN Review Complete - Prod 6/04 • 90 day look back file specs • Epic access has been approved for Elevate – Template Creation has been finalized |  | • Review and revise plan |  | None
Status Legend
C | Complete
G | On Track
Y | At Risk
R | Significant Risk w/ inadequate mitigation
NS | Not Started

## Status Report Key
Status Report Key
Attribute | Definition
Red (R) | One or more of the following conditions exist: Phase/Milestone is at significant risk of delay. Multiple issues or risks exist, no mitigation plans in place. Schedule: Major date of delivery slippage is expected; > 2-week variance. Resource: Resource availability certain to impact project; >10% variance from projection. Deliverable % Complete: Major deliverables are completed with >2-week variance of planned duration. Budget: Cost variance >5% beyond contingency plan and progress inhibited.
Yellow (Y) | One or more of the following conditions exist and none of the above conditions exist: Phase/Milestone is at risk of missing date of delivery. Active issues or risks exist, mitigation plan(s) in development. Schedule: ~30% probability minor date of delivery slippage, <2-week variance. Resource: Resource availability may impact date of delivery; 1-9% variance from projection. Deliverable % Complete: Major deliverables and milestones completed on schedule with <2-week variance. Budget: Cost variance >5% beyond contingency plan and progress not yet inhibited or expecting a cost variance within the next two weeks.
Green (G) | Project is on track as indicated by all the following conditions existing: Phase/Milestone is tracking to planned date of delivery. No unmitigated issues or risks. Resource: No resource constraints that will impact date of delivery. Deliverable % Complete: Major deliverables and milestones completed on schedule with <1-week variance. Schedule: Delivery dates are expected to be on time. Budget: No cost variance currently or anticipated within the next two weeks.
Not Started (NS) | Task/deliverable has not started yet.
Complete (C) | Task/deliverable is complete.

## Email Instructions
PPR Email Communication Instructions
Purpose: Create a consistent and standardized PPR email communication to our stakeholders.
Steps:
1. Copy and paste template to your email.
2. Insert Project Name.
3. Determine appropriate status and delete all others.
4. Add maximum of two impactful accomplishments, next steps, and issues.
5. If you do not have any since the last PPR, list “none”.
6. Insert link to Teams Site.
Email Template
Hello,
Please see attached <Insert Project Name Here> Project Report Out (PPR).
Status: Complete, On Track, At Risk, Significant Risk w/ inadequate mitigation
Accomplishments:
XX
XX
Next Steps:
XX
XX
Issues:
XX
XX
For additional detailed information, visit the Teams Site. Please reach out with any questions you may have.
Thank you,